## Roadmap
FIELDFLICKS
Targeted Features Roadmap
Sprint plan · 16-20 Jun 2026 · Update Status to track progress
# | Feature | Description | Status | Owner | Target Date | Notes
1 | Points for Recordings | Foundational reward — every recording earns the user 5 points. | Completed | Engineering | 15 Jun 2026 | Shipped Mon 15 Jun.
2 | Share Incentives | Sharer +2 pts, recipient +1 pt — drives organic distribution. | Completed | Engineering | 15 Jun 2026 | Backend + FE wired.
3 | Discount Coupons | Coupon codes apply to base price; user-side picker on payment. | Completed | Engineering | 16 Jun 2026 | Pre-GST discount confirmed.
4 | Profile Image | Avatar upload + crop on Profile. | Completed | Frontend | 16 Jun 2026 | S3-backed upload live.
5 | Top Performer Rewards | Weekly + monthly leaderboard winners get recording discounts. | In Progress | Backend | 17 Jun 2026 | Cron + assignment rules in dev.
6 | Payment Filters | Filter payment history by date, status, and sport. | In Progress | Frontend | 17 Jun 2026 | UI 80% — needs sport chip polish.
7 | Game Card | Personalised, shareable game card per session. | In Progress | Design + FE | 18 Jun 2026 | Card template review pending.
8 | Player Levels | Tiered progression (Bronze → Diamond) based on points. | Pending | Backend | 18 Jun 2026 | Spec finalised; build starts Wed.
9 | Event Organisation | Organise multi-court tournaments + ad-hoc events. | Pending | Full team | 19 Jun 2026 | Scoping doc due Wed AM.
At a glance | Completed | 4 | In Progress | 3 | Pending | 2 | Total | 9